## ReadMe_Notes
Important: The Analysis ToolPak Add-in must be turned on (under Tools > Add Ins)
Enter your Task names, Owners, Start Dates and duration in Days in the white cells.
The grey cells contain formulas that will calculate automatically along with the GANTT chart.
The Summary tasks (shown in Blue) use Max() and Min() functions to add up the duration of the sub-tasks below.
To link tasks together so they run consecutively, you can use simple formulas
e.g. choose a cell in column E and set the start_date of one task = end_date of the previous task.
You can of course just type in the Start date for any task if it is already known (Fixed planning)
FTEs is the Full Time Equivalent, so 1 for one person, 2 for 2 people, 0.5 for one person working half the day etc
Hrs will multiply the number of Days by FTEs to give the total hours worked on each task.
Changing the number of staff or the hours worked will not automatically adjust the task finish time.
HOLIDAYS
Make sure the holiday worksheet has the correct bank holiday dates for your country.
It is helpfull to also format the relevant cells in row 1 to indicate bank holidays
(you can also use this row to indicate key project milestones)
NOTES
One thing the s/sheet will not attempt to do is reconcile overbooked resources
e.g. if you assign Fred to perform 10 one day tasks, all starting on the same day,
the spreadsheet will not extend the task durations just because Fred is overbooked.
To add extra rows, just copy and paste - the easiest way is to insert rows (Insert Menu) and copy entire rows
so that you get all the formulas for the Gantt chart.
The spreadsheet assumes that no-one will work on weekends or bank holidays.
Column A can be used to allocate WBS numbers, which you can tie into other project paperwork. (this is optional)
Protection is off, to protect the formulas from accidental typos, look under Tools, Protection.
In Excel 2003 (or Excel Mac) the spreadsheet width is limited to 36 Weeks (256 columns),
in Excel 2007 you can copy the formulas out horizontally to plot up to 45 years (16384 columns)

## Project_Plan_Gantt
2008-05-01 | [7 empty] | Holidays & Meetings:
WBS |  | Tasks | Owner | Plan Start | Days | Finish | FTEs | Hrs. | 2008-05-05 | [6 empty] | 2008-05-12 | [6 empty] | 2008-05-19 | [6 empty] | 2008-05-26 | [6 empty] | 2008-06-02 | [6 empty] | 2008-06-09 | [6 empty] | 2008-06-16 | [6 empty] | 2008-06-23 | [6 empty] | 2008-06-30 | [6 empty] | 2008-07-07 | [6 empty] | 2008-07-14 | [6 empty] | 2008-07-21 | [6 empty] | 2008-07-28 | [6 empty] | 2008-08-04 | [6 empty] | 2008-08-11 | [6 empty] | 2008-08-18 | [6 empty] | 2008-08-25 | [6 empty] | 2008-09-01 | [6 empty] | 2008-09-08 | [6 empty] | 2008-09-15 | [6 empty] | 2008-09-22 | [6 empty] | 2008-09-29 | [6 empty] | 2008-10-06 | [6 empty] | 2008-10-13 | [6 empty] | 2008-10-20 | [6 empty] | 2008-10-27 | [6 empty] | 2008-11-03 | [6 empty] | 2008-11-10 | [6 empty] | 2008-11-17 | [6 empty] | 2008-11-24 | [6 empty] | 2008-12-01 | [6 empty] | 2008-12-08 | [6 empty] | 2008-12-15 | [6 empty] | 2008-12-22
1 | My Demo Project | [6 empty] | 984.8 | 2008-05-05 | 2008-05-06 | 2008-05-07 | 2008-05-08 | 2008-05-09 | 2008-05-10 | 2008-05-11 | 2008-05-12 | 2008-05-13 | 2008-05-14 | 2008-05-15 | 2008-05-16 | 2008-05-17 | 2008-05-18 | 2008-05-19 | 2008-05-20 | 2008-05-21 | 2008-05-22 | 2008-05-23 | 2008-05-24 | 2008-05-25 | 2008-05-26 | 2008-05-27 | 2008-05-28 | 2008-05-29 | 2008-05-30 | 2008-05-31 | 2008-06-01 | 2008-06-02 | 2008-06-03 | 2008-06-04 | 2008-06-05 | 2008-06-06 | 2008-06-07 | 2008-06-08 | 2008-06-09 | 2008-06-10 | 2008-06-11 | 2008-06-12 | 2008-06-13 | 2008-06-14 | 2008-06-15 | 2008-06-16 | 2008-06-17 | 2008-06-18 | 2008-06-19 | 2008-06-20 | 2008-06-21 | 2008-06-22 | 2008-06-23 | 2008-06-24 | 2008-06-25 | 2008-06-26 | 2008-06-27 | 2008-06-28 | 2008-06-29 | 2008-06-30 | 2008-07-01 | 2008-07-02 | 2008-07-03 | 2008-07-04 | 2008-07-05 | 2008-07-06 | 2008-07-07 | 2008-07-08 | 2008-07-09 | 2008-07-10 | 2008-07-11 | 2008-07-12 | 2008-07-13 | 2008-07-14 | 2008-07-15 | 2008-07-16 | 2008-07-17 | 2008-07-18 | 2008-07-19 | 2008-07-20 | 2008-07-21 | 2008-07-22 | 2008-07-23 | 2008-07-24 | 2008-07-25 | 2008-07-26 | 2008-07-27 | 2008-07-28 | 2008-07-29 | 2008-07-30 | 2008-07-31 | 2008-08-01 | 2008-08-02 | 2008-08-03 | 2008-08-04 | 2008-08-05 | 2008-08-06 | 2008-08-07 | 2008-08-08 | 2008-08-09 | 2008-08-10 | 2008-08-11 | 2008-08-12 | 2008-08-13 | 2008-08-14 | 2008-08-15 | 2008-08-16 | 2008-08-17 | 2008-08-18 | 2008-08-19 | 2008-08-20 | 2008-08-21 | 2008-08-22 | 2008-08-23 | 2008-08-24 | 2008-08-25 | 2008-08-26 | 2008-08-27 | 2008-08-28 | 2008-08-29 | 2008-08-30 | 2008-08-31 | 2008-09-01 | 2008-09-02 | 2008-09-03 | 2008-09-04 | 2008-09-05 | 2008-09-06 | 2008-09-07 | 2008-09-08 | 2008-09-09 | 2008-09-10 | 2008-09-11 | 2008-09-12 | 2008-09-13 | 2008-09-14 | 2008-09-15 | 2008-09-16 | 2008-09-17 | 2008-09-18 | 2008-09-19 | 2008-09-20 | 2008-09-21 | 2008-09-22 | 2008-09-23 | 2008-09-24 | 2008-09-25 | 2008-09-26 | 2008-09-27 | 2008-09-28 | 2008-09-29 | 2008-09-30 | 2008-10-01 | 2008-10-02 | 2008-10-03 | 2008-10-04 | 2008-10-05 | 2008-10-06 | 2008-10-07 | 2008-10-08 | 2008-10-09 | 2008-10-10 | 2008-10-11 | 2008-10-12 | 2008-10-13 | 2008-10-14 | 2008-10-15 | 2008-10-16 | 2008-10-17 | 2008-10-18 | 2008-10-19 | 2008-10-20 | 2008-10-21 | 2008-10-22 | 2008-10-23 | 2008-10-24 | 2008-10-25 | 2008-10-26 | 2008-10-27 | 2008-10-28 | 2008-10-29 | 2008-10-30 | 2008-10-31 | 2008-11-01 | 2008-11-02 | 2008-11-03 | 2008-11-04 | 2008-11-05 | 2008-11-06 | 2008-11-07 | 2008-11-08 | 2008-11-09 | 2008-11-10 | 2008-11-11 | 2008-11-12 | 2008-11-13 | 2008-11-14 | 2008-11-15 | 2008-11-16 | 2008-11-17 | 2008-11-18 | 2008-11-19 | 2008-11-20 | 2008-11-21 | 2008-11-22 | 2008-11-23 | 2008-11-24 | 2008-11-25 | 2008-11-26 | 2008-11-27 | 2008-11-28 | 2008-11-29 | 2008-11-30 | 2008-12-01 | 2008-12-02 | 2008-12-03 | 2008-12-04 | 2008-12-05 | 2008-12-06 | 2008-12-07 | 2008-12-08 | 2008-12-09 | 2008-12-10 | 2008-12-11 | 2008-12-12 | 2008-12-13 | 2008-12-14 | 2008-12-15 | 2008-12-16 | 2008-12-17 | 2008-12-18 | 2008-12-19 | 2008-12-20 | 2008-12-21 | 2008-12-22 | 2008-12-23 | 2008-12-24 | 2008-12-25 | 2008-12-26 | 2008-12-27 | 2008-12-28
1.1 | Project planning & prep |  |  | 2008-05-12 | - | 2008-08-26 | - | bar: Hrs. 984.8; 2008-05-12 2008-05-12 to 2008-08-25 2008-08-26
1.1.1 |  | Supervison & coord | Liz | 2008-05-12 | 75 | 2008-08-26 | 0.4 | Hrs. 984.8: 240; 2008-05-12 2008-05-12: 1; 2008-05-12 2008-05-13: 1; 2008-05-12 2008-05-14: 1; 2008-05-12 2008-05-15: 1; 2008-05-12 2008-05-16: 1; 2008-05-12 2008-05-17: 1; 2008-05-12 2008-05-18: 1; 2008-05-19 2008-05-19: 1; 2008-05-19 2008-05-20: 1; 2008-05-19 2008-05-21: 1; 2008-05-19 2008-05-22: 1; 2008-05-19 2008-05-23: 1; 2008-05-19 2008-05-24: 1; 2008-05-19 2008-05-25: 1; 2008-05-26 2008-05-26: 1; 2008-05-26 2008-05-27: 1; 2008-05-26 2008-05-28: 1; 2008-05-26 2008-05-29: 1; 2008-05-26 2008-05-30: 1; 2008-05-26 2008-05-31: 1; 2008-05-26 2008-06-01: 1; 2008-06-02 2008-06-02: 1; 2008-06-02 2008-06-03: 1; 2008-06-02 2008-06-04: 1; 2008-06-02 2008-06-05: 1; 2008-06-02 2008-06-06: 1; 2008-06-02 2008-06-07: 1; 2008-06-02 2008-06-08: 1; 2008-06-09 2008-06-09: 1; 2008-06-09 2008-06-10: 1; 2008-06-09 2008-06-11: 1; 2008-06-09 2008-06-12: 1; 2008-06-09 2008-06-13: 1; 2008-06-09 2008-06-14: 1; 2008-06-09 2008-06-15: 1; 2008-06-16 2008-06-16: 1; 2008-06-16 2008-06-17: 1; 2008-06-16 2008-06-18: 1; 2008-06-16 2008-06-19: 1; 2008-06-16 2008-06-20: 1; 2008-06-16 2008-06-21: 1; 2008-06-16 2008-06-22: 1; 2008-06-23 2008-06-23: 1; 2008-06-23 2008-06-24: 1; 2008-06-23 2008-06-25: 1; 2008-06-23 2008-06-26: 1; 2008-06-23 2008-06-27: 1; 2008-06-23 2008-06-28: 1; 2008-06-23 2008-06-29: 1; 2008-06-30 2008-06-30: 1; 2008-06-30 2008-07-01: 1; 2008-06-30 2008-07-02: 1; 2008-06-30 2008-07-03: 1; 2008-06-30 2008-07-04: 1; 2008-06-30 2008-07-05: 1; 2008-06-30 2008-07-06: 1; 2008-07-07 2008-07-07: 1; 2008-07-07 2008-07-08: 1; 2008-07-07 2008-07-09: 1; 2008-07-07 2008-07-10: 1; 2008-07-07 2008-07-11: 1; 2008-07-07 2008-07-12: 1; 2008-07-07 2008-07-13: 1; 2008-07-14 2008-07-14: 1; 2008-07-14 2008-07-15: 1; 2008-07-14 2008-07-16: 1; 2008-07-14 2008-07-17: 1; 2008-07-14 2008-07-18: 1; 2008-07-14 2008-07-19: 1; 2008-07-14 2008-07-20: 1; 2008-07-21 2008-07-21: 1; 2008-07-21 2008-07-22: 1; 2008-07-21 2008-07-23: 1; 2008-07-21 2008-07-24: 1; 2008-07-21 2008-07-25: 1; 2008-07-21 2008-07-26: 1; 2008-07-21 2008-07-27: 1; 2008-07-28 2008-07-28: 1; 2008-07-28 2008-07-29: 1; 2008-07-28 2008-07-30: 1; 2008-07-28 2008-07-31: 1; 2008-07-28 2008-08-01: 1; 2008-07-28 2008-08-02: 1; 2008-07-28 2008-08-03: 1; 2008-08-04 2008-08-04: 1; 2008-08-04 2008-08-05: 1; 2008-08-04 2008-08-06: 1; 2008-08-04 2008-08-07: 1; 2008-08-04 2008-08-08: 1; 2008-08-04 2008-08-09: 1; 2008-08-04 2008-08-10: 1; 2008-08-11 2008-08-11: 1; 2008-08-11 2008-08-12: 1; 2008-08-11 2008-08-13: 1; 2008-08-11 2008-08-14: 1; 2008-08-11 2008-08-15: 1; 2008-08-11 2008-08-16: 1; 2008-08-11 2008-08-17: 1; 2008-08-18 2008-08-18: 1; 2008-08-18 2008-08-19: 1; 2008-08-18 2008-08-20: 1; 2008-08-18 2008-08-21: 1; 2008-08-18 2008-08-22: 1; 2008-08-18 2008-08-23: 1; 2008-08-18 2008-08-24: 1; 2008-08-25 2008-08-25: 1; 2008-08-25 2008-08-26: 1
1.1.2 |  | Develop plan | Liz | 2008-05-14 | 12 | 2008-05-30 | 0.3 | Hrs. 984.8: 28.8; 2008-05-12 2008-05-14: 1; 2008-05-12 2008-05-15: 1; 2008-05-12 2008-05-16: 1; 2008-05-12 2008-05-17: 1; 2008-05-12 2008-05-18: 1; 2008-05-19 2008-05-19: 1; 2008-05-19 2008-05-20: 1; 2008-05-19 2008-05-21: 1; 2008-05-19 2008-05-22: 1; 2008-05-19 2008-05-23: 1; 2008-05-19 2008-05-24: 1; 2008-05-19 2008-05-25: 1; 2008-05-26 2008-05-26: 1; 2008-05-26 2008-05-27: 1; 2008-05-26 2008-05-28: 1; 2008-05-26 2008-05-29: 1; 2008-05-26 2008-05-30: 1
1.1.3 |  | Develop budget | Bill | 2008-05-24 | 11 | 2008-06-10 | 0.2 | Hrs. 984.8: 17.6; 2008-05-19 2008-05-24: 1; 2008-05-19 2008-05-25: 1; 2008-05-26 2008-05-26: 1; 2008-05-26 2008-05-27: 1; 2008-05-26 2008-05-28: 1; 2008-05-26 2008-05-29: 1; 2008-05-26 2008-05-30: 1; 2008-05-26 2008-05-31: 1; 2008-05-26 2008-06-01: 1; 2008-06-02 2008-06-02: 1; 2008-06-02 2008-06-03: 1; 2008-06-02 2008-06-04: 1; 2008-06-02 2008-06-05: 1; 2008-06-02 2008-06-06: 1; 2008-06-02 2008-06-07: 1; 2008-06-02 2008-06-08: 1; 2008-06-09 2008-06-09: 1; 2008-06-09 2008-06-10: 1
1.1.4 |  | Schedule kickoff mtg. | Simon | 2008-05-17 | 1 | 2008-05-19 | 0.2 | Hrs. 984.8: 1.6; 2008-05-12 2008-05-17: 1; 2008-05-12 2008-05-18: 1; 2008-05-19 2008-05-19: 1
1.1.5 |  | Conduct kickoff mtg. | Jim | 2008-06-07 | 0 | 2008-06-06 | 8 | Hrs. 984.8: 0
1.2.1 | Conduct requirements analysis |  |  | 2008-05-24 | - | 2008-07-15 | - | bar: Hrs. 984.8; 2008-05-19 2008-05-24 to 2008-07-14 2008-07-15
|  | Develop interview forms | Bob | 2008-05-24 | 5 | 2008-06-02 | 2 | Hrs. 984.8: 80; 2008-05-19 2008-05-24: 1; 2008-05-19 2008-05-25: 1; 2008-05-26 2008-05-26: 1; 2008-05-26 2008-05-27: 1; 2008-05-26 2008-05-28: 1; 2008-05-26 2008-05-29: 1; 2008-05-26 2008-05-30: 1; 2008-05-26 2008-05-31: 1; 2008-05-26 2008-06-01: 1; 2008-06-02 2008-06-02: 1
|  | Conduct interviews | Gordon | 2008-06-02 | 3 | 2008-06-04 | 4 | Hrs. 984.8: 96; 2008-06-02 2008-06-02: 1; 2008-06-02 2008-06-03: 1; 2008-06-02 2008-06-04: 1
|  | Write prelim. requirements | Simon | 2008-06-30 | 5 | 2008-07-07 | 1 | Hrs. 984.8: 40; 2008-06-30 2008-06-30: 1; 2008-06-30 2008-07-01: 1; 2008-06-30 2008-07-02: 1; 2008-06-30 2008-07-03: 1; 2008-06-30 2008-07-04: 1; 2008-06-30 2008-07-05: 1; 2008-06-30 2008-07-06: 1; 2008-07-07 2008-07-07: 1
|  | Conduct walk-thru | Jim | 2008-07-07 | 2 | 2008-07-08 | 8 | Hrs. 984.8: 128; 2008-07-07 2008-07-07: 1; 2008-07-07 2008-07-08: 1
|  | Update requirements doc. | Jim | 2008-07-08 | 6 | 2008-07-15 | 2 | Hrs. 984.8: 96; 2008-07-07 2008-07-08: 1; 2008-07-07 2008-07-09: 1; 2008-07-07 2008-07-10: 1; 2008-07-07 2008-07-11: 1; 2008-07-07 2008-07-12: 1; 2008-07-07 2008-07-13: 1; 2008-07-14 2008-07-14: 1; 2008-07-14 2008-07-15: 1
1.2.2 | Establish requirements baseline |  |  | 2008-07-15 | - | 2008-08-05 | - | bar: Hrs. 984.8; 2008-07-14 2008-07-15 to 2008-08-04 2008-08-05
|  | Publish draft req. doc. | Simon | 2008-07-15 | 1 | 2008-07-15 | 1 | Hrs. 984.8: 8; 2008-07-14 2008-07-15: 1
|  | Conduct req. review mtg. | Gordon | 2008-07-19 | 2 | 2008-07-22 | 8 | Hrs. 984.8: 128; 2008-07-14 2008-07-19: 1; 2008-07-14 2008-07-20: 1; 2008-07-21 2008-07-21: 1; 2008-07-21 2008-07-22: 1
|  | Incorporate comments | Dave | 2008-07-26 | 5 | 2008-08-01 | 2 | Hrs. 984.8: 80; 2008-07-21 2008-07-26: 1; 2008-07-21 2008-07-27: 1; 2008-07-28 2008-07-28: 1; 2008-07-28 2008-07-29: 1; 2008-07-28 2008-07-30: 1; 2008-07-28 2008-07-31: 1; 2008-07-28 2008-08-01: 1
|  | Send document for signatures | Gordon | 2008-08-02 | 2 | 2008-08-05 | 1 | Hrs. 984.8: 16; 2008-07-28 2008-08-02: 1; 2008-07-28 2008-08-03: 1; 2008-08-04 2008-08-04: 1; 2008-08-04 2008-08-05: 1
|  | Establish formal baseline | Mel | 2008-08-03 | 1 | 2008-08-04 | 0.1 | Hrs. 984.8: 0.8; 2008-07-28 2008-08-03: 1; 2008-08-04 2008-08-04: 1
| Next Major WBS Element |  |  | 2008-06-16 | - | 2008-06-30 | - | bar: Hrs. 984.8; 2008-06-16 2008-06-16 to 2008-06-30 2008-06-30
|  | Task |  | 2008-06-16 | 3 | 2008-06-18 | 1 | Hrs. 984.8: 24; 2008-06-16 2008-06-16: 1; 2008-06-16 2008-06-17: 1; 2008-06-16 2008-06-18: 1
|  | Task |  | 2008-06-18 | 3 | 2008-06-20 | 0 | Hrs. 984.8: 0; 2008-06-16 2008-06-18: 1; 2008-06-16 2008-06-19: 1; 2008-06-16 2008-06-20: 1
|  | Task |  | 2008-06-20 | 3 | 2008-06-24 | 0 | Hrs. 984.8: 0; 2008-06-16 2008-06-20: 1; 2008-06-16 2008-06-21: 1; 2008-06-16 2008-06-22: 1; 2008-06-23 2008-06-23: 1; 2008-06-23 2008-06-24: 1
|  | Task |  | 2008-06-24 | 3 | 2008-06-26 | 0 | Hrs. 984.8: 0; 2008-06-23 2008-06-24: 1; 2008-06-23 2008-06-25: 1; 2008-06-23 2008-06-26: 1
|  | Task |  | 2008-06-26 | 3 | 2008-06-30 | 0 | Hrs. 984.8: 0; 2008-06-23 2008-06-26: 1; 2008-06-23 2008-06-27: 1; 2008-06-23 2008-06-28: 1; 2008-06-23 2008-06-29: 1; 2008-06-30 2008-06-30: 1
| Next Major WBS Element |  |  | 2008-06-30 | - | 2008-07-29 | - | bar: Hrs. 984.8; 2008-06-30 2008-06-30 to 2008-07-28 2008-07-29
|  | Task |  | 2008-06-30 | 5 | 2008-07-07 | 0 | Hrs. 984.8: 0; 2008-06-30 2008-06-30: 1; 2008-06-30 2008-07-01: 1; 2008-06-30 2008-07-02: 1; 2008-06-30 2008-07-03: 1; 2008-06-30 2008-07-04: 1; 2008-06-30 2008-07-05: 1; 2008-06-30 2008-07-06: 1; 2008-07-07 2008-07-07: 1
|  | Task |  | 2008-07-07 | 5 | 2008-07-11 | 0 | Hrs. 984.8: 0; 2008-07-07 2008-07-07: 1; 2008-07-07 2008-07-08: 1; 2008-07-07 2008-07-09: 1; 2008-07-07 2008-07-10: 1; 2008-07-07 2008-07-11: 1
|  | Task |  | 2008-07-11 | 5 | 2008-07-17 | 0 | Hrs. 984.8: 0; 2008-07-07 2008-07-11: 1; 2008-07-07 2008-07-12: 1; 2008-07-07 2008-07-13: 1; 2008-07-14 2008-07-14: 1; 2008-07-14 2008-07-15: 1; 2008-07-14 2008-07-16: 1; 2008-07-14 2008-07-17: 1
|  | Task |  | 2008-07-17 | 5 | 2008-07-23 | 0 | Hrs. 984.8: 0; 2008-07-14 2008-07-17: 1; 2008-07-14 2008-07-18: 1; 2008-07-14 2008-07-19: 1; 2008-07-14 2008-07-20: 1; 2008-07-21 2008-07-21: 1; 2008-07-21 2008-07-22: 1; 2008-07-21 2008-07-23: 1
|  | Task |  | 2008-07-23 | 5 | 2008-07-29 | 0 | Hrs. 984.8: 0; 2008-07-21 2008-07-23: 1; 2008-07-21 2008-07-24: 1; 2008-07-21 2008-07-25: 1; 2008-07-21 2008-07-26: 1; 2008-07-21 2008-07-27: 1; 2008-07-28 2008-07-28: 1; 2008-07-28 2008-07-29: 1
| Next Major WBS Element |  |  | 2008-07-29 | - | 2008-08-05 | - | bar: Hrs. 984.8; 2008-07-28 2008-07-29 to 2008-08-04 2008-08-05
|  | Task |  | 2008-07-29 | 2 | 2008-07-30 | 0 | Hrs. 984.8: 0; 2008-07-28 2008-07-29: 1; 2008-07-28 2008-07-30: 1
|  | Task |  | 2008-07-30 | 2 | 2008-07-31 | 0 | Hrs. 984.8: 0; 2008-07-28 2008-07-30: 1; 2008-07-28 2008-07-31: 1
|  | Task |  | 2008-07-31 | 2 | 2008-08-01 | 0 | Hrs. 984.8: 0; 2008-07-28 2008-07-31: 1; 2008-07-28 2008-08-01: 1
|  | Task |  | 2008-08-01 | 2 | 2008-08-04 | 0 | Hrs. 984.8: 0; 2008-07-28 2008-08-01: 1; 2008-07-28 2008-08-02: 1; 2008-07-28 2008-08-03: 1; 2008-08-04 2008-08-04: 1
|  | Task |  | 2008-08-04 | 2 | 2008-08-05 | 0 | Hrs. 984.8: 0; 2008-08-04 2008-08-04: 1; 2008-08-04 2008-08-05: 1
| Next Major WBS Element |  |  | 2008-08-05 | - | 2008-09-03 | - | bar: Hrs. 984.8; 2008-08-04 2008-08-05 to 2008-09-01 2008-09-03
|  | Task |  | 2008-08-05 | 5 | 2008-08-11 | 0 | Hrs. 984.8: 0; 2008-08-04 2008-08-05: 1; 2008-08-04 2008-08-06: 1; 2008-08-04 2008-08-07: 1; 2008-08-04 2008-08-08: 1; 2008-08-04 2008-08-09: 1; 2008-08-04 2008-08-10: 1; 2008-08-11 2008-08-11: 1
|  | Task |  | 2008-08-11 | 5 | 2008-08-15 | 0 | Hrs. 984.8: 0; 2008-08-11 2008-08-11: 1; 2008-08-11 2008-08-12: 1; 2008-08-11 2008-08-13: 1; 2008-08-11 2008-08-14: 1; 2008-08-11 2008-08-15: 1
|  | Task |  | 2008-08-15 | 5 | 2008-08-21 | 0 | Hrs. 984.8: 0; 2008-08-11 2008-08-15: 1; 2008-08-11 2008-08-16: 1; 2008-08-11 2008-08-17: 1; 2008-08-18 2008-08-18: 1; 2008-08-18 2008-08-19: 1; 2008-08-18 2008-08-20: 1; 2008-08-18 2008-08-21: 1
|  | Task |  | 2008-08-21 | 5 | 2008-08-27 | 0 | Hrs. 984.8: 0; 2008-08-18 2008-08-21: 1; 2008-08-18 2008-08-22: 1; 2008-08-18 2008-08-23: 1; 2008-08-18 2008-08-24: 1; 2008-08-25 2008-08-25: 1; 2008-08-25 2008-08-26: 1; 2008-08-25 2008-08-27: 1
|  | Task |  | 2008-08-27 | 5 | 2008-09-03 | 0 | Hrs. 984.8: 0; 2008-08-25 2008-08-27: 1; 2008-08-25 2008-08-28: 1; 2008-08-25 2008-08-29: 1; 2008-08-25 2008-08-30: 1; 2008-08-25 2008-08-31: 1; 2008-09-01 2008-09-01: 1; 2008-09-01 2008-09-02: 1; 2008-09-01 2008-09-03: 1
Note: Calendar week dates begin on Mondays.

## Holidays
Holidays for All Staff | Length of Working Day
2008-05-26 | 8 | hours
2008-07-04
2008-09-01
2008-10-13
Enter company/bank holidays in the green box
This is actually a 'named range' called "Holidays"
If you need more space, just add a row (Insert,Rows) to the middle of the box
The Gantt chart will calculate end_dates by adding Start_Date + DURATION skipping the holidays above.